**INTAROS Executive Board Meeting No. 37**

Date: 04 June 2021 10:00 – 12:30 CET

Via GoToMeeting

***Minutes and actions***

Participants: S. Sandven, H. Sagen, G. Ottersen, R. Pirazzini, A. B. Moller, F. Danielsen, R.Higgins, T. Hamre, E. Buch, T. Kurschke (partly), P. Goncalves (partly), K. Lygre, H. Sagen, A. Solgaard, A. Ahlstrøm, P. Voss, M. Sørensen, T. Johannessen, S. Quegan, L. Iversen (partly), D. Gustavson, E. Asmi,

The meeting was recorded and is available at : <https://www.dropbox.com/s/c19dyzpidae99ui/2021-06-04%2010.02%20INTAROS%20Executive%20board%20meeting%20.mp4?dl=0>

Meeting leader: S. Sandven

|  |  |  |  |
| --- | --- | --- | --- |
| No | Description | Deadline | Comments |
| 1 | The status of the deliverables due in 2021 was updated. The overview document showing the status of each deliverable is available at <https://www.dropbox.com/home/INTAROS-Deliverables-2021> |  |  |
| 2 | Extension of the project period by three months. All partners have confirmed that they approve this extension. The coordinator has contacted the project officer about the extension and initiated a contract amendment: The amendment requires updated   * Dates of deliverables that are delayed * Change in workplan description where there were changes due toCOVID-19 * Change in budget between labour cost and other costs etc.   The PIs for each partner is responsible for providing this information |  |  |
| 3 | Video material for dissemination of INTAROS activities and results was discussed. A list of existing videos as well as plans for new videos are shown in Appendix 1 |  |  |
| 4 | Status of the booklet and info sheets. The review is done for almost all 55 sheets. A few more are expected. Will be sent to the company for second print during the next month |  |  |
| 5 | Input to the periodic report is required from all partners during June. Kjetil will give further instruction about deadlines |  |  |
| 6 | Upcoming activities: There will be a UAK-INTAROS cruise with KV Svalbard from 5 to 18 June. The cruise includes a research school for MSc and PhD students in ocean observing field techniques. |  |  |
|  | Next EB meeting: 05 July |  |  |

**Conferences, workshops and other events with INTAROS participation (from 01 Jan 2021)**

|  |  |  |  |
| --- | --- | --- | --- |
| Date | Meeting | Participants from INTAROS | Comment |
| **2021** |  |  |  |
| 12-13 Jan | INTAROS General Assembly, online | All partners |  |
| 20 January | Stakeholder seminar – marine ecosystems and fisheries management, organized by IMR. Report is available at <https://intaros.nersc.no/content/stakeholder-seminar-marine-resources-and-fisheries-management> | IMR, AU |  |
| 4 – 16 February | Dialogue meetings with Research Infrastructures: Hydrosphere, Atmosphere, Geosphere and Biosphere | EuroGOOS – Erik Buch |  |
| 23-24 February | Scientific workshop on optimal use of operational satellite microwave products for high latitudes and polar area models. Link: https://www.eventsforce.net/eumetsat/frontend/reg/thome.csp?pageID=9185&eventID=21&traceRedir=2 | Georg Heygster gave presentation |  |
|  |  |  |  |
| 24-26 March | ASSW21: INTAROS representations |  |  |
|  | Session ID 60 dedicated to INTAROS: 6 oral and 4 posters | ≈10 INTAROS part |  |
|  | Session ID 25: Oral presentation by Stein | Stein, Olivia |  |
|  | Session ID 85: Oral presentation by Lisbeth + poster | Lisbeth, Hajo, Finn, Noor |  |
| 27-30 April | EGU:  Michael Poulsen: Monitoring Svalbard’s Environment and cultural heritage through citizen science by expedition cruises https://doi.org/10.5194/egusphere-egu21-15951  Kjetil Lygre: et al. Float Your Boat Norway (poster in session EOS7.3) https://doi.org/10.5194/egusphere-egu21-16269,  Torill Hamre et al., A standards Data Catalogue integrating scientific, community-based and citizen science data across the Arctic (poster in session ESSI3.3), https://doi.org/10.5194/egusphere-egu21-15783 |  |  |
| 01 June | Stakeholder meeting on West Greenland ecosystem patterns and drivers, online meeting | Organized by AU and GINR |  |
| 22-27 June | ASLO 2021 Aquatic Sciences meeting – virtual meeting: https://www.isp.cnr.it/index.php/en/eventi2/item/447-aslo-2021-aquatic-sciences-meeting-22-27-june-2021-virtual-meeting | Presentation by AU |  |

**Appendix 1: Video material**

**Existing video material from INTAROS work**

|  |  |  |  |
| --- | --- | --- | --- |
| Partners |  |  | Status |
| NERSC | INTAROS presentation at KO - music only - 6 min |  |  |
|  | KV Svalbard field experiment in 2018 – 16 min | https://www.youtube.com/watch?v=WWC\_XfO7Lc8 | Good overview |
|  | INTAROS 2018 trailer – music only 3 min | https://www.youtube.com/watch?v=m0JQQS6asSw&t=18s |  |
|  |  |  |  |
| UIB GEO | OBS cruise in 2019 ACC Mosby – 5:52 min | https://www.youtube.com/watch?v=U6ch88KY9Dk&t=20s |  |
|  | Instruction to use the INTAROS data catalogue: Christian Rønnevik 9:23 min | https://www.youtube.com/watch?v=h3qLJt-Mpmw | Example from seismology |
| UIB GFI | From INTAROS 2018 cruise: Isotope measurements – Alexandra Touzeau | <https://vimeo.com/286842288> |  |
| GEUS | Andreas Ahlstrøm: Field work in Greenland 2019: 4:50 min | https://www.youtube.com/watch?v=Y4wx4SvZ8XE&t=42s | Good overview |
| GINR | Working in the field – marine monitoring in Greenland, 3 min | https://www.youtube.com/watch?v=Q\_JALhAO96U |  |
| IGPAN | Collection of 8 videos under “INTAROS project” including three short presentations of students in Hornsund | https://www.youtube.com/channel/UCoegF3QSQe17mmGvj8oNs\_g |  |
|  | **Webinars** |  |  |
| IGPAN | Scientix webinar 1 hour: How to inspire students for Arctic careers - INTAROS toolkits for schools | <https://www.youtube.com/watch?v=u7Mka2TAbHs> | Toolkits for schools |
|  |  |  |  |
|  | **From INTAROS General Assembly** | Videos are available of all presentations on 12-13 January :  <https://intaros.nersc.no/content/video-recording-presentations-general-assembly-2021> |  |
|  | **From ASSW 24-26 March** |  |  |
|  | 5 min videos on |  |  |
| NERSC | Stein: selected INTAROS work | Mp4 video available |  |
| IGPAN | Agata: on education | Mp4 video available |  |
| U Alaska | Hajo: on community based systems | Mp4 video available |  |
|  |  |  |  |

**Planned videos 2021:**

|  |  |  |  |
| --- | --- | --- | --- |
| NERSC | From UAK cruise with KV Svalbard: interviews, educational videos on use of instruments on the ice. |  |  |
| NORDECO | We are happy to provide short videos about our work in the project. We can provide some of this material when you need it (kindly let us know 1-2 weeks in advance, some of this is already available on youtube and vimeo under the heading “PISUNA”), and we are also planning to make new videos this spring and summer, amongst other from mini-drones, these video materials could be available by the end of August (or earlier if needed from your end, depending also somewhat on the pandemic and the opening up of travels) |  |  |
| FMI | 2 videos are planned for educational use, replacement for the summer school which was cancelled |  |  |
| SMHI | Similar video as for the HYPE-ERAS project:  <https://youtu.be/mJ3w-MgRuWQ> |  |  |
| TDUE | iAOS showcase applications in collaboration with WP6 partners, first with IMR (CTD data, Task 6.2), then SMHI (end Sept) and the others |  |  |
| IMR | Geir suggested to provide something from IMR activities. |  |  |
| USFD | Dona: video from field work in Alaska |  |  |
|  |  |  |  |
|  |  |  |  |