## Slide 1: INTAROS Steering Committee 07 June 2017 0900 - 1600
IOPAN Sopot

## Slide 2: Agenda items
Minutes and actions from previous SC-meeting
Deliverables in the first 6 months
Experience with EMdesk for periodic reporting
Status of work performed in the WPs, incl survey in WP2
First stakeholder workshop in Brussels on 5 May
Website status
Members of the advisory boards
Risk management
Collaboration with other projects
Draft MoU with CAA

## Slide 3: Item 2: Actions from SC meeting 10 Jan
Action no | Description | Status
17-01 | Propose relevant stakeholders with justification to E. Buch for participation in the workshop on 5 May, hosted by the EuroGOOS office in Brussels | OK, see list of invited persons to the Stakeholder workshop
17-02 | Set up the first stakeholder group for INTAROS, which will be expanded during the project | OK, as above
17-03 | Prepare Terms of Reference for the two advisory panels | OK, see D8.3
17-04 | EB will define procedures for establishing formal collaboration with other projects | in progress, see agenda item 14
17-05 | Provide comments to Sandra and Ned in order to finalize the brochure | OK
17-06 | Members of the SC should propose students or other persons in their organisation who could help to use social media. Send names to Ned | Status ?
17-07 | The coordination team shall propose a risk management procedure as part of the project management system. | in progress, see agenda item 13

## Slide 4: Item 6: Stakeholder workshop on 5 May
Invited representatives from key organisations and stakeholder groups: SAON, AMAP, EEA, EU-PolarNET, SIOS, YOPP, ACTRIS, CMEMS, ICES, WGMS, INTERACT
Addressing high-level questions on observing systems:
(1) Coordination and collaboration between data providers and stakeholders in the pan-Arctic region in order to better use existing systems and resources
(2) Improvement of the observing platforms and sensors, filling of gaps in the observing network and facilitate for year-round operation
(3) Data sampling, transmission, calibration, processing, archiving and retrieval of required variables and building distributed and connected databases
(4) How to develop sustainability of the observing systems

## Slide 5: Item 13: Risk management: identify risk factors and mitigation actions (1)
Description of risk | WP involved | Proposed mitigation actions
Lack of interest among relevant stakeholders (low) | WP1, WP6, WP7 | Enhance communication with more stakeholders, organise more stakeholder workshops,
Lack of connectivity between WPs and delays in deliverables (low) | All WPs | Proactive management by coordinator and WP-leaders. Raise issues at SC- and EB-meetings and decide on mitigation
Lack of interest among key partners to establish Pan-Arctic Observing Forum (low) | WP1 | Ensure that Pan-Arctic Observing Forum is closely connected to existing network and can offer benefits to members. Mitigation: Start to work with SAON committes
Lack of long-term funding of observing systems (Medium-high) | WP1 | Involve funding agencies and stakeholders from the start. Build on existing international frameworks (SAON, GEO, Copernicus, etc.)
Lack of agreement on data sharing principles and data standards (Low) | WP1, WP2 | Work closely with other Arctic data management experts and committees (i.e. through ADC) to resolve issues

## Slide 6: Item 13: Risk management: identify risk factors and mitigation actions (2)
Description of risk | WP involved | Proposed mitigation actions
Access to data from Russia (Low-Medium) | WP2 | Involve Russian partners (NIERSC and RIHMI) who have relevant data. Funding for the Russian partners is open, so this risk is real
Access to ice-going vessel for deployment and recovery of instruments (Low) | WP3 | Several partners in the consortium have access to ice-going vessels, which will be present in the Arctic (AWI, IMR, MISU), incl. icebreakers from China and South Korea.
Loss of equipment or failure to function resulting in loss of data (Low-Medium) | WP3 | Robust and well-proven platforms and technologies are used to minimize the risk for failure. Design of experiments according to the highest standards.
Hindrances in translating community data into decision-making (Medium) | WP4, WP6 | Will integrate community-based data into international databases and actively promote the use of the results for decision-making. Need to establish best-practices

## Slide 7: Item 13: Risk management: identify risk factors and mitigation actions (3)
Description of risk | WP involved | Proposed mitigation actions
Integration challenges when accessing existing Arctic data repositories (Low-Medium) | WP5 WP6 | Leading experts will jointly work to define standard protocols and metadata to enable technical integration. Each repository to be integrated has a partner with the needed technical expertise to integrate it into iAOS.
Scalability or usability issues with the iAOS Cloud Platform reduces the benefits for stakeholders (Low) | WP5 WP6 | The Terradue Cloud Platform has solid expertise in processing large amounts of satellite data and extract geophysical parameters. Experience will be used to help the scientists in the project to develop useful services for WP6.
Loss or late/low availability of key personnel (Low) | All | Transfer responsibilities (and if necessary funds) between partners if a partner with shortage of personnel cannot hire qualified candidates within a reasonable time frame to meet the project schedule.

## Slide 8: Item 14: Collaboration with other projects and SAON
Projects | How to collaborate, what kind of agreement
EU Polar projects: | Establish Task Groups on (1) Stakeholder engagament, (2) Communication, (3) Data Management between EU-PolarNet, Blue Action, APPLICATE, ARC-ICE, and INTERACT
Other EU projects and infrastructures | AtlantOS, ENVRI PLUS: collaboration stated in GA, attended meetings, but no concrete plan yet
ESA Polar TEP | Prepared a note on collaboration between INTAROS and Polar TEP (attached). Will include BAS and PolarView as cooperating partners in the next contract amendment
INTAROS partners outside Europe | Dialogue and several meetings with institutions in USA, Canada, Russia, China, Japan, South Korea. Partners of INTAROS have signed Consortium Agreement (except PRIC), other insitutions can join later as cooperarting partners.

## Slide 9: Item 15: Task groups members from INTAROS
Task Group | Members from INTAROS (proposed)
Stakeholder engagement | Stein Sandven/Erik Buch
Communication | Ned Dwyer/?
Data management | Pedro Goncalves/Torill Hamre
INTAROS members of the Task groups should be appointed by the Steering Committee.

## Slide 10: Item 16: MoU with PRIC and CAA
  CAA (Chinese Arctic and Antarctic Administration) will coordinate Arctic expeditions with the Chinese icebreaker Xue Long in 2018 and probably in 2019 and onwards. China will also have a second icebreaker ready for Arctic operation in from 2019.
  PRIC is responsinble for the logistics of the expedtions
  INTAROS can participate in the Chinese expeditions for deployment of ITPs and IMBs under WP3. An agreement (MoU) is in preparation.

## Slide 11: Milestones (year 1 and 2)
No | Milestone name | WPs | Month | Means of verification
1 | First workshop with stakeholders and INTAROS consortium partners | All WPs | 3 | Minutes of the workshop
2 | Initial requirement report | WP1 | 6 | Report available on the website (D1.1). Responsible: EuroGOOS
3 | Assessment and gap analysis of present observing systems | WP2 | 18 | 3 reports available on website: ocean and sea ice (resp. UHAM), atmosphere (resp. MISU) and terrestrial-cryosphere (resp. USFD)
4 | New sensors and platforms ready for deployment | WP3 | 18 | Deployments are verified by the responsible Task leaders: Greenland (GEUS), North Svalbard (UiB), Fram Strait (AWI), Arctic Ocean (IOPAN), Siberia (MPG), Alaska (OU), Canada (CNRS)
5 | Data repositories available for accessing data | WP2 | 24 | First set of data available for the iAOS platform. Responsible data providers: ocean and sea ice (AWI), atmosphere (GFZ), terr./cryosphere (FMI)
6 | Prototype iAOS platform in operation | WP5 | 24 | Test of iAOS platform functionality. Resp. TERRADUE
15 | Pan-Arctic Observing Forum established | WP1 | 24 | Agreement document: D1.4 (MoU, Terms of reference)

## Slide 12: INTAROS presentations autumn 2016
5-7 Sept: YOPP planning meeting, ECMWF Reading UK (S. Sandven, Y. Gao)
5-7 Sept: The 5th Nordic ENVRI workshop on Arctic RI collaboration, Longyearbyen (H. Sagen)
14 Sept: Polar Day in Bergen (Hanne Sagen)
07 Oct: Polar Circle, Iceland: Session: Operational Marine Service in the Arctic (A. B. Möller, S. Sandven)
17 Oct: Visit to ONR in Washington (H. Sagen, S. Sandven)
18 Oct: MEOPAR expert meeting in Ottawa (S. Sandven)
08 Nov: Presentation at Research Council of Norway, Oslo (H. Sagen, S. Sandven)
08 Nov: GEO Plenary, St. Petersburg, side meeting of GEOCRI (L. H. Pettersson)
08-09 Nov: Polar Connections Interoperability Workshop at ESRIN (T. Hamre - participant)
10-11 Nov: YOPP data meeting, Oslo (T. Hamre)
12 Nov: COP22, Marakesch, Arctic Day organized by Nordic Council of Ministers (H. Sagen)
16-17 Nov: ENVRI-Copernicus meeting in Prague (H. Sagen)
17 Nov: Norwegian Scientific Academy for Polar Research, Bergen (S. Sandven)
12-16 Dec: Poster presentation at AGU, San Fransisco (S. Sandven, H. Sagen)

## Slide 13: Presentation of INTAROS in 2017 (1)
Date | Event | Attended by
11-12 Jan | KO-meeting in Bergen with invited guests | ≈ all partners
18-19 Jan | Presented INTAROS at Blue Action KO-meeting, Berlin | S. Sandven, Y. Gao
25 Jan | Meeting with ArCS director M Fukusaw at Arctic Frontier | S. Sandven
8-9 Feb | APPLICSATE KO-meeting, Berlin | S. Sandven
16 Feb | Presented INTAROS at Ministry of Env and Climate | S. Sandven
27 Feb – 01 March | Invitation to PPP SG Meeting and the YOPP Buoys and Floats Task Team, Maryland | A. B. Möller
01-06 March | Visited and presented INTAROS to Chinese partners (PRIC in Shanghai, RADI and NMEFC in Beijing) | S. Sandven, Y. Gao
29-30 March | Arctic Workshop of the Transatlantic Ocean Research Alliance, Brussels, collaboration USA and Canada | S. Sandven, H. Sagen
3 April | EU-Polarnet GA meeting in Prague | S. Sandven, H. Sagen
4-7 April | Arctic Science Summit Week (ASSW), poster presentation | S. Sandven, H. Sagen, T. Hamre
7 April | Invited to SAON Board meeting | S. Sandven, H. Sagen, T. Hamre

## Slide 14: Presentations of INTAROS in 2017 (2)
Date | Event | 
23-28 April | EGU session "Cross Disciplinary Observations for an Integrated Understanding of the Arctic System” | A. B. Möller presented poster
24 – 28 April | International Conference on Arctic Science: Bringing Knowledge to Action Reston, Virginia, oral and poster | A. Ahlström presented
Date | Event | 
23-28 April | EGU session "Cross Disciplinary Observations for an Integrated Understanding of the Arctic System” | A. B. Möller presented poster
24 – 28 April | International Conference on Arctic Science: Bringing Knowledge to Action Reston, Virginia, oral and poster | A. Ahlström presented
05 May | INTAROS Stakeholder Workshop in Brussel, 25 invited participants, several partners from INTAROS | Hosted by EuroGOOS
8-10 May | OceaNoise 2017. Invited presentation on data management of acoustic data | T. Hamre and H. Sagen (co-chair )
8 - 12 May | Arctic Interchange, Week of the Arctic, Fairbanks, including workshop on community based observing | Finn Danielsen, Hajo Eicken
23-24 May | Modelling workshop, Brussels, coordination between Blue Action, APPLICATE, INTAROS and others | Virgnie Guemas
30 May | Meeting in Norwegian Research Council on H2020, Oslo | S. Sandven
31 May | EuroGOOS General Assembly, Brussel | S. Sandven
11-15 June | ESSAS Open Science Meeting on Subarctic and Arctic Science (http://www.imr.no/essas/en) | G. Ottersen
11–16 June | POAC 2017 in Busan, South Korea | S. Sandven
19-21 June | 11th GEO European Projects Workshop, Helsinki | S. Sandven, E. Buch